## Slide 1: Editorial Advisory Group Plan for concepts representing role
Toni Morrison, Sr. Terminologist
2016-02-29

## Slide 2: Plan for concepts representing role
Concepts representing role need to be removed from the Pharmaceutical / biologic product Hierarchy
  Inclusion of these concepts in the Product Hierarchy results in overloaded |Is a| relationships and clinically incorrect inferred referred relationships.
  Inclusion of these primitive concepts in the Product Hierarchy results in the inability to fully define large numbers of Medicinal Entity and Medicinal Form concepts using sound modeling practices.
  The association between a concept describing a product and a product role represents knowledge that is outside of the scope of SNOMED CT.
  Product role may vary across Member countries.

## Slide 3: Plan for concepts representing role, cont.
Inactivation of concepts representing role will begin for July 2016 release and be completed in January 2017 release
  Grouper concepts will be systematically reviewed to identify concepts that represent product role (cursory review suggests n ≈ 1200)
    A log listing concepts that have been inactivated, and possibly concepts that were reviewed and will be retained, will be available to Members via Confluence
  A small number of grouper concepts that do not represent product role but that cannot be fully defined will also be addressed as part of this project.
  Concepts will be inactivated as |Erroneous| OR |Outdated| with a |WAS A| relationship to |Pharmaceutical / biologic product (product)|.

## Slide 4: Roles future plans
A new method of creating and using concepts representing roles in SNOMED CT is needed. This work will be addressed in a separate project.
Inactivation of concepts representing role is already underway in the Substance Hierarchy
  First stage completed for the January 2016 release