## Slide 1: Lessons learned – GP/FP project

## Slide 2: Project outline
The overall purpose of this project was to create two interdependent products:
  A general/family practice RefSet of the SNOMED CT concepts most frequently used in general/family practice internationally – scope agreed was reasons for Encounter and Health Issues.
  A map from the SNOMED CT GP/FP RefSet to ICPC-2.
Project approach
  Development of the project framework (including scope, requirements, methodology and tooling)
  Construction of the GP/FP RefSet
  Construction of the map from the RefSet to ICPC-2.

## Slide 3: Lessons learned – project (1)
Define your use case
Clear methodology
Managing source data - need for additional rules/principles not recognised in methodology
The importance of clinical governance – do not underestimate the commitment required
Tooling – relied heavily on the availability of 3 tools: creating term sets, developing maps and field testing tool, leading to:
  coordination issues
  access delays due to interdependencies with external providers outside IHTSDO control
  Versioning problems
Knowledge of SNOMED CT – structure and technical aspects
Time – severe under estimation of time for the project (planned 21 months, took 40 months)

## Slide 4: Lessons learned – project (2)
Time – severe under estimation of time for the project (planned 21 months, took 40 months)
  the amount of time needed to map the source termsets to SNOMED CT (which took double the amount of time expected)
  the time needed for clinical review of each version of the RefSet
  delays in starting the map from the GP/FP RefSet to ICPC-2, which could not be started until the GP/FP RefSet had been completed
  the time needed to map the concepts in the GP/FP RefSet to ICPC-2, and to perform quality assurance on the map through the IHTSDO map lead and resolution process.
  Delays in access to tools
Field test
  Underestimated the willingness for GPs/FPs to participate with no incentive.
  Recruitment strategy is key to include consideration of incentives
  Additions to tool not anticipated

## Slide 5: Lessons learned - IHTSDO
Timelines
Securing clinical input when using volunteers
Establishing from the outset the full set of IHTSDO resources required to complete the project and move to publication and maintenance
Tooling requirements established from the beginning and within IHTSDO control